## Vulnerability Tracker
VULNERABILITY TRACKER — Production Environment
CVE ID | CVSS | Severity | Host / Asset | Service | Port | Description | Discovery Date | SLA Deadline | Status | Remediation
CVE-2023-44487 | 7.5 | High | 10.1.1.10 (web01) | nginx | 443 | HTTP/2 Rapid Reset DoS vulnerability in nginx < 1.25.3 | 2024-01-05 | 2024-02-04 | Open | Upgrade nginx to 1.25.3 or later
CVE-2023-23397 | 9.8 | Critical | 10.1.1.20 (mail01) | Outlook | 445 | Microsoft Outlook privilege escalation via UNC path in email | 2024-01-07 | 2024-01-22 | In Progress | Apply MS patch KB5023280; block outbound SMB at firewall
CVE-2022-47966 | 9.8 | Critical | 10.1.1.30 (mgmt01) | ManageEngine | 443 | RCE in ManageEngine ServiceDesk via SAML authentication | 2024-01-10 | 2024-01-25 | Remediated | Upgraded to ServiceDesk Plus 14003
CVE-2023-35078 | 10 | Critical | 10.1.1.40 (mdm01) | Ivanti MDM | 443 | Auth bypass in Ivanti Endpoint Manager Mobile (EPMM) | 2024-01-12 | 2024-01-27 | Open | Apply Ivanti patch per vendor advisory EPMM-2023-001
CVE-2023-4966 | 9.4 | Critical | 10.1.1.50 (citrix01) | Citrix ADC | 443 | Sensitive info disclosure in Citrix ADC and Gateway | 2024-01-15 | 2024-01-30 | Open | Apply CTX-2023-0007 patch; invalidate active sessions
CVE-2023-28252 | 7.8 | High | 10.1.1.60 (dc01) | Windows OS | N/A | Windows CLFS driver privilege escalation vulnerability | 2024-01-18 | 2024-02-17 | Open | Apply KB5025229 patch via WSUS
CVE-2023-20269 | 5 | Medium | 10.1.1.70 (vpn01) | Cisco ASA | 443 | Brute-force vulnerability in Cisco ASA SSL VPN | 2024-01-20 | 2024-04-20 | Open | Enable AAA lockout; implement MFA for VPN access
CVE-2023-27997 | 9.2 | Critical | 10.1.1.80 (fw01) | FortiGate | 443 | Heap overflow in FortiOS SSL-VPN pre-authentication RCE | 2024-01-22 | 2024-02-06 | Remediated | Upgraded FortiOS to 7.4.1
CVE-2022-41082 | 8.8 | High | 10.1.1.90 (ex01) | Exchange | 443 | Microsoft Exchange Server RCE via PowerShell remoting | 2024-01-25 | 2024-02-24 | In Progress | Apply KB5019758; disable remote PS if not needed
CVE-2023-32315 | 7.5 | High | 10.1.1.100 (chat01) | Openfire | 9090 | Path traversal in Openfire admin console authentication | 2024-01-28 | 2024-02-27 | Open | Upgrade Openfire to 4.7.5 or apply workaround
CVE-2023-3519 | 9.8 | Critical | 10.1.1.110 (gw01) | Citrix ADC | 443 | Unauthenticated RCE in Citrix ADC NSAPI | 2024-02-01 | 2024-02-16 | Open | Apply CTX-2023-0052 immediately; check for IOCs
CVE-2023-26360 | 8.6 | High | 10.1.1.120 (cms01) | Adobe CF | 8500 | Improper access control in Adobe ColdFusion | 2024-02-03 | 2024-03-04 | Open | Apply APSB23-25 patch; restrict CF admin access
SUMMARY | [5 empty] | 8 | Open findings | 6 | Critical